MERIDIAN ADVISORY GROUP

# The Meridian Way

Our Consulting Methodology & Delivery Framework

INTERNAL — CONFIDENTIAL

## Overview

The Meridian Way is our proprietary consulting methodology that governs how we engage with clients, structure our delivery, and ensure consistent quality across all engagements. Developed over a decade of delivery across 600+ engagements, the methodology codifies the practices that separate high-performing advisory from commodity consulting.

Every Meridian engagement follows this framework regardless of service line, adapting the depth and duration of each phase to the engagement scope and complexity.

## Phase 1: Discovery & Alignment (Weeks 1-3)

Before we prescribe, we listen. The Discovery phase establishes a shared understanding of the client's current state, strategic objectives, constraints, and success criteria. We conduct structured stakeholder interviews, review existing documentation and data, and map the organizational and technical landscape.

Key activities:

Executive sponsor alignment session (2 hours) — confirm objectives, constraints, and success metrics

Stakeholder interview series (8-15 interviews depending on scope) — capture perspectives across leadership, operations, and technology

Current state assessment — technology landscape, data architecture, process mapping, organizational structure

Constraint mapping — budget, timeline, regulatory, contractual, and change capacity limitations

Discovery findings synthesis — consolidated view delivered as a 10-page findings brief

Deliverable: Discovery Findings Brief with validated problem statement and confirmed scope.

## Phase 2: Analysis & Design (Weeks 3-6)

The Analysis phase translates discovery findings into a structured solution design. We evaluate options against the client's constraints, model business cases with quantified ROI, and design the target architecture, operating model, or implementation plan.

Key activities:

Options analysis with weighted scoring against client criteria

Business case development with 3-year ROI model (conservative, expected, optimistic scenarios)

Target state architecture or operating model design

Risk assessment and mitigation planning

Implementation roadmap with phased delivery milestones

Governance framework design

Deliverable: Recommendations Report with business case, target state design, and phased implementation roadmap.

## Phase 3: Build & Implement (Weeks 6-16+)

For implementation engagements, Meridian deploys integrated delivery teams using agile methodology adapted for enterprise consulting. We run 2-week sprints with formal client demos, maintain a visible delivery backlog, and track progress against the business outcomes defined in Phase 2 — not just technical milestones.

Key activities:

Sprint-based delivery with 2-week cycles and client demos

Weekly engagement health check (scope, budget, timeline, quality, risk)

Bi-weekly executive steering committee briefing

Change management and stakeholder communication

Technical implementation, configuration, integration, and testing

User acceptance testing and training

## Phase 4: Stabilize & Transfer (Weeks 14-18+)

We don't declare victory and leave. The Stabilize phase ensures the client's team can independently operate and evolve what we built. We provide structured knowledge transfer, hypercare support, and a 90-day post-deployment health check.

Key activities:

Knowledge transfer sessions with client operations and technology teams

Runbook and operational documentation creation

30-day hypercare support with dedicated Meridian resources

90-day post-deployment health check and optimization review

Lessons learned capture and client satisfaction survey

## Quality Assurance Standards

Every Meridian engagement is subject to our quality assurance framework, which includes:

Named engagement partner accountable for client outcomes (not just project delivery)

Weekly engagement health scoring across 5 dimensions: scope adherence, budget tracking, timeline confidence, quality metrics, and risk register

Peer review of all major deliverables by a senior practitioner not on the engagement team

Client satisfaction pulse checks at Phase 2 and Phase 4 milestones

Post-engagement retrospective within 2 weeks of close

## Engagement Governance

| Governance Element | Frequency | Participants |
| --- | --- | --- |
| Sprint demo | Bi-weekly | Delivery team + client project team |
| Engagement health review | Weekly | Engagement manager + partner |
| Executive steering committee | Bi-weekly | Partner + client executive sponsor |
| Quality gate review | Per phase | Engagement partner + peer reviewer |
| Risk escalation | As needed | Managing Director within 24 hours |